CIVIS

Sovereign Diaspora Intelligence Platform

Onboarding &

Implementation Playbook

Version 1.0

Prepared by Afronovation, Inc.

Classification: Internal Operations — Confidential

# Document Information

| Document Title | Onboarding & Implementation Playbook |
| --- | --- |
| Version | 1.0 |
| Status | Foundational Operations Document |
| Classification | Internal Operations — Confidential |
| Prepared By | Afronovation, Inc. |
| Audience | Commercial Team, Implementation Team, Customer Success, Engineering |
| EmbassyOS Note | Embassy workspace built standalone in Phase 1. Full EmbassyOS integration in a subsequent phase. |
| Platform | Civis Sovereign Intelligence Platform |

# 1. Purpose & Scope

This playbook defines the complete government onboarding and implementation sequence for the Civis Sovereign Intelligence Platform. It covers every step from contract execution through go-live, including tenant provisioning, data migration, embassy setup, staff training, and the first registration campaign.

This document is used by the Afronovation implementation team when deploying a new sovereign client, by the customer success team when managing the onboarding relationship, and by government IT and programme teams as a reference for their own preparation and readiness.

Implementation Philosophy A successful Civis onboarding is not measured by whether the platform is technically live — it is measured by whether the government is independently operating a growing registry with confidence. Technical deployment is the beginning, not the end, of a successful onboarding. Every implementation must conclude with government staff who can operate the platform, understand the intelligence it generates, and build on it independently.

# 2. Implementation Overview

## 2.1 Implementation Phases

| Phase 1 — Pre-Implementation | Contract execution, legal and compliance review, data residency confirmation, infrastructure provisioning planning, and government team readiness assessment. Duration: 2–4 weeks. |
| --- | --- |
| Phase 2 — Technical Setup | Tenant provisioning, environment configuration, data residency verification, branding configuration, and domain setup. Duration: 1–2 weeks. |
| Phase 3 — Data Migration | Migration of existing embassy registries, spreadsheets, or legacy registry data into the Civis data model. Duration: 1–6 weeks depending on source format and volume. |
| Phase 4 — Embassy Setup | Embassy profile creation, jurisdiction configuration, staff account provisioning, and embassy workspace validation. Duration: 1–2 weeks. |
| Phase 5 — Training | Role-specific training for all government platform users — Tenant Admin, Embassy Admin, Consular Officers, Analysts, and Executive Viewers. Duration: 1 week. |
| Phase 6 — Go-Live & First Campaign | Platform go-live, first registration campaign launch, and initial performance monitoring. Duration: ongoing from go-live. |
| Phase 7 — Hypercare | Intensive post-launch support period. Weekly check-ins, rapid issue resolution, and performance optimisation. Duration: 4–8 weeks post-go-live. |
| Phase 8 — Steady State | Handover to standard customer success support. Quarterly business reviews. Annual renewal and expansion planning. Duration: ongoing. |

## 2.2 Typical Implementation Timeline

| Civis Cloud — Standard | 8–12 weeks from contract execution to go-live. No legacy data migration: 6–8 weeks. |
| --- | --- |
| Civis Government — Standard | 10–14 weeks from contract execution to go-live. Dedicated infrastructure adds 1–2 weeks. |
| Civis Sovereign — Full | 14–20 weeks from contract execution to go-live. Dedicated infrastructure provisioning and data residency verification add 4–6 weeks. |

# 3. Phase 1 — Pre-Implementation

| # | Step | Owner | Actions & Deliverables |
| --- | --- | --- | --- |
| 1.1 | Contract & DPA Execution | Commercial + Legal | Sovereign client agreement executed. Data Processing Agreement signed. Deployment tier confirmed. Payment terms agreed. |
| 1.2 | Data Residency Assessment | Legal + Engineering | Client country's applicable data protection laws reviewed. Hosting region selected. Data residency preference documented in civis_tenants.data_residency_region. |
| 1.3 | Government Team Identification | Customer Success | Government identifies: Tenant Admin (primary platform owner), Embassy Admins (per embassy), IT contact (technical liaison), Programme Director (executive sponsor). |
| 1.4 | Existing Data Assessment | Implementation Team | Government provides inventory of existing diaspora data — spreadsheets, database exports, embassy files. Migration complexity assessed. Migration approach agreed. |
| 1.5 | Infrastructure Planning | DevOps + Engineering | For Civis Government/Sovereign: hosting region confirmed, infrastructure provisioning plan prepared, Timeline agreed with government IT team. |
| 1.6 | Branding Requirements | Design + Implementation | Government provides: official logo files, colour codes, official platform name (if custom branding required for Civis Government/Sovereign), domain name preference. |
| 1.7 | Pre-Implementation Checklist | Implementation Lead | Complete pre-implementation checklist (see Section 7). Sign-off from both Afronovation and government programme director before Phase 2 begins. |

# 4. Phase 2 — Technical Setup

| # | Step | Owner | Actions & Deliverables |
| --- | --- | --- | --- |
| 2.1 | Tenant Provisioning | Platform Engineering | civis_tenants record created. deployment_tier, data_residency_region, default_language, and supported_languages configured. Tenant status set to 'pilot' until go-live. |
| 2.2 | Tenant Settings Configuration | Platform Engineering | civis_tenant_settings configured: consent language (EN and/or FR), registration mode, verification requirements, MFA requirements per role, data export permissions. |
| 2.3 | Infrastructure Deployment | DevOps | Civis Cloud: standard tenant onboarding. Civis Government: dedicated Vercel project deployed. Civis Sovereign: Terraform IaC applied, dedicated PostgreSQL and storage provisioned. |
| 2.4 | Data Residency Verification | DevOps + Legal | Infrastructure team verifies data is being written to the correct regional database. Cross-region data transfer test executed. Written confirmation provided to government IT team. |
| 2.5 | Branding Configuration | Design + Engineering | Civis Government/Sovereign: national branding applied, platform name configured, logo integrated into dashboard header and login page. |
| 2.6 | Domain Configuration | DevOps | Custom domain configured and DNS pointed to Civis infrastructure. TLS certificate issued. Redirect from staging URL to production domain configured. |
| 2.7 | Tenant Admin Account | Platform Engineering | Sovereign Tenant Admin account created. MFA enrolled. Temporary credentials delivered via secure channel (encrypted email or secure link). Password change required on first login. |
| 2.8 | Technical Validation | Implementation Lead | Technical setup checklist completed (see Section 7). Platform Admin and government IT contact jointly verify all configuration before data migration begins. |

# 5. Phase 3 — Data Migration

Data migration is one of the most variable and risk-sensitive phases of implementation. The approach depends entirely on the format, quality, and volume of the government's existing diaspora data. There is no single migration playbook — each migration is designed after the existing data assessment in Phase 1.

## 5.1 Migration Source Formats

| Source Format | Description | Migration Approach | Timeline Estimate |
| --- | --- | --- | --- |
| Excel/CSV Registries | Most common format. Direct import via Civis data migration service. Field mapping required. | Field mapping worksheet provided. Afronovation team maps source fields to civis_registrants schema. Duplicate detection applied. | 1–3 weeks depending on volume and data quality. |
| Embassy Spreadsheets | Per-embassy Excel or Google Sheets files. Often inconsistent column names across embassies. | Consolidation and normalisation step required before import. Embassy jurisdiction assignment applied during migration. | 2–4 weeks. Complexity depends on number of embassies and format consistency. |
| Legacy Database Export | SQL or structured database export. Higher data fidelity but requires schema mapping. | ETL process designed by Afronovation engineering. Data residency verified before transfer. Test migration on staging before production. | 3–6 weeks. Requires technical resource from government IT team. |
| Manual Entry (No Existing Data) | No prior digital records. Registry built from scratch via registration campaigns. | No migration required. Embassy workspace and registration portal activated. First registration campaign planned as part of onboarding. | Ongoing — no migration timeline. |
| Paper Records | Physical registration cards or paper embassy forms. Requires manual digitisation. | Afronovation does not provide digitisation services. Government must digitise to CSV/Excel first. Digitisation support can be scoped as professional services. | Variable. Digitisation lead time outside Afronovation scope. |

## 5.2 Standard Migration Process

| # | Step | Owner | Actions & Deliverables |
| --- | --- | --- | --- |
| 3.1 | Data Export from Source | Government IT | Government exports existing registry data in the agreed format — typically CSV or Excel. Sensitive data transferred via secure channel (SFTP or encrypted file transfer). |
| 3.2 | Data Quality Assessment | Implementation Team | Afronovation reviews exported data for completeness, consistency, and quality. Duplicate records flagged. Missing required fields identified. Quality report shared with government team. |
| 3.3 | Field Mapping | Implementation Team | Source fields mapped to civis_registrants schema. Mapping document reviewed and approved by government Tenant Admin before migration proceeds. |
| 3.4 | Test Migration — Staging | Implementation Team | 100–500 records migrated to staging environment. Government Tenant Admin reviews migrated records for accuracy. Field mapping adjusted if required. |
| 3.5 | Full Migration — Staging | Implementation Team | Complete dataset migrated to staging environment. Duplicate detection run. Quality scores calculated. Government reviews sample records across embassies. |
| 3.6 | Government Sign-off | Government Tenant Admin | Government Tenant Admin reviews migration results and signs off on data accuracy. Any corrections agreed and applied before production migration. |
| 3.7 | Production Migration | Implementation Team | Approved data migrated to production environment. Migration audit log generated. Record count verified against source. Government notified of completion. |
| 3.8 | Post-Migration Validation | Implementation + Government | Government Tenant Admin spot-checks migrated records. Embassy Admins verify records in their jurisdictions. Data quality scores reviewed. Any issues resolved within 5 business days. |

Data Privacy During Migration All data transferred during migration is treated as Restricted Personal Data per the data classification model. Transfer occurs via encrypted channels only. Data is imported directly to the production or staging environment — never stored on Afronovation staff personal devices or unencrypted shared storage. Migration activities are logged in the audit trail.

# 6. Phase 4 — Embassy Setup

Embassy setup is a critical onboarding phase that directly determines the quality of geographic intelligence and the accuracy of jurisdiction-based access controls. Every embassy must be configured before Embassy Admin and Consular Officer accounts are created.

EmbassyOS Integration Note In Phase 1, the Civis embassy workspace operates as a fully functional standalone module. Full integration with the EmbassyOS diplomatic operations platform — enabling shared consular workflows, appointment scheduling, and citizen identity synchronisation — is planned for a subsequent phase. Embassy setup in Phase 1 creates the data structures and access controls that will serve as the foundation for the EmbassyOS integration when it is activated.

| # | Step | Owner | Actions & Deliverables |
| --- | --- | --- | --- |
| 4.1 | Embassy Inventory | Government Tenant Admin | Government provides complete list of embassies, consulates, high commissions, and other diplomatic missions. Each mission identified with: name, mission type, host country, host city, and estimated diaspora coverage area. |
| 4.2 | Embassy Record Creation | Implementation Team | civis_embassies records created for each mission. mission_type, host_country, host_city, address, and contact details populated. Status set to active. |
| 4.3 | Jurisdiction Configuration | Implementation Team + Government | Geographic coverage boundaries defined for each embassy in civis_embassy_jurisdictions. Country, state/region, and city coverage mapped. Overlapping jurisdictions reviewed and resolved with government. |
| 4.4 | Embassy Admin Accounts | Platform Engineering | Embassy Admin accounts created for each mission. MFA enrolled. Accounts scoped to correct embassy jurisdiction. Temporary credentials delivered securely. |
| 4.5 | Consular Officer Accounts | Embassy Admin | Embassy Admin creates Consular Officer accounts for their mission. Role assignments scoped to embassy jurisdiction. Accounts activated after training completion. |
| 4.6 | Embassy Workspace Validation | Embassy Admin + Implementation | Each Embassy Admin verifies their workspace is correctly configured. Jurisdiction boundaries tested. Test registrant created and confirmed to appear in correct embassy scope. |
| 4.7 | Registrant Association | Platform Engineering | Migrated registrants associated with correct embassy based on country of residence and jurisdiction mapping. Association results reviewed by Embassy Admins. |

# 7. Phase 5 — Training Programme

Training is delivered role-specifically — each government staff member is trained only on the platform functionality relevant to their role. Over-training creates confusion; under-training creates dependency on Afronovation support.

## 7.1 Training Schedule

Training is delivered in the following sequence to ensure each role can build on the previous session. All training is available in English and French.

| Week 1 — Day 1 | Tenant Admin training. Full platform overview, configuration, user management, and governance. |
| --- | --- |
| Week 1 — Day 2 | Embassy Admin training. Embassy workspace, verification workflow, campaign management. |
| Week 1 — Day 3 | Consular Officer training. Registration workflow, document review, queue management. |
| Week 1 — Day 4 | Analyst and Economic Planner training. Dashboards, Dia AI, reports, data export. |
| Week 1 — Day 5 | Executive Viewer orientation. Dashboard overview, Dia insight reading, report access. |
| Week 2 | Hands-on practice period. Government team operates platform independently with Afronovation available for questions. Issues logged and resolved. |

## 7.2 Role-Specific Training Specifications

| Role | Topics Covered | Duration & Format | Delivery Method |
| --- | --- | --- | --- |
| Tenant Admin | Platform overview and sovereign intelligence value. Tenant configuration and governance controls. User and role management. Embassy management. Audit log access and compliance review. Report generation and executive briefing workflow. | 4 hours total. 2 x 2-hour sessions. Remote or in-person. | Platform Admin walkthrough. Hands-on configuration workshop. Q&A session. |
| Embassy Admin | Embassy workspace overview. Registrant management and verification workflow. Jurisdiction configuration. Campaign management. Embassy dashboard and analytics. | 3 hours total. 1 x 3-hour session. Remote or in-person. | Embassy workspace walkthrough. Verification workflow simulation. Campaign creation exercise. |
| Consular Officer | Registration creation workflow. Profile completion and document metadata. Verification queue management. Basic embassy analytics. | 2 hours total. 1 x 2-hour session. Remote preferred. | Hands-on registration workflow. Document review simulation. |
| Analyst | Analytics dashboard navigation. Dia AI query interface. Geographic intelligence and map interpretation. Report generation. Data export workflow. | 3 hours total. 1 x 3-hour session. Remote preferred. | Dashboard navigation exercise. Dia query workshop. Report generation hands-on. |
| Economic Planner | Economic intelligence dashboards. Remittance and investment analytics. Dia bond readiness interpretation. Forecasting dashboard review. | 2 hours total. 1 x 2-hour session. | Economic dashboard walkthrough. Dia forecast interpretation exercise. |
| Executive Viewer | Executive dashboard overview. Metric card interpretation. Dia insight card reading. Report access and download. | 1 hour. 1 x 1-hour session. Remote preferred. | Dashboard orientation. Dia insight walkthrough. Report access demonstration. |

## 7.3 Training Deliverables

- Training documentation delivered in EN and FR — platform user guides, quick reference cards, and FAQ documents

- Video walkthrough recordings provided for each role — available for onboarding future staff

- Training completion certificates issued to all trained government staff

- Platform sandbox environment available for continued practice post-training

- Afronovation support channel active for 4 weeks post-training for questions

# 8. Phase 6 — Go-Live & First Registration Campaign

| # | Step | Owner | Actions & Deliverables |
| --- | --- | --- | --- |
| 6.1 | Go-Live Readiness Review | Implementation Lead + Government | All checklist items verified (see Section 11). Government Tenant Admin confirms platform is operationally ready. Afronovation Implementation Lead signs off. |
| 6.2 | Tenant Status Activation | Platform Engineering | civis_tenants status updated from 'pilot' to 'active'. Platform fully operational. Monitoring dashboards activated. |
| 6.3 | Public Portal Activation | Engineering + Government | Diaspora registrant portal activated. Public URL confirmed. Registration form tested end-to-end in both EN and FR. Consent text verified in correct language. |
| 6.4 | First Campaign Planning | Customer Success + Government | First registration campaign designed with government programme team. Target diaspora segment identified. Outreach channel strategy agreed (embassy networks, diaspora associations, social media, government diaspora portals). |
| 6.5 | Campaign Creation | Government Tenant Admin | Registration drive campaign created in Civis campaign module. Target segment configured. Campaign messaging approved in EN and FR. Activation date set. |
| 6.6 | Campaign Launch | Government Programme Team | Campaign activated. Outreach to diaspora community begins through agreed channels. Embassy teams briefed and ready to assist registrants. |
| 6.7 | Go-Live Monitoring — Week 1 | Customer Success + Engineering | Daily monitoring of registration volume, error rates, and platform performance. Any issues escalated immediately. Government team provided daily activity summary. |

# 9. Phase 7 — Hypercare Support Period

The Hypercare period runs for 4–8 weeks following go-live. During this period, Afronovation provides enhanced support to ensure the government team is confident, the platform is performing as expected, and the first registration campaign is on track.

| Weekly Check-in Calls | Weekly 30-minute call between Afronovation Customer Success and government Tenant Admin. Platform performance review, registration growth tracking, issue resolution, and next-step planning. |
| --- | --- |
| Priority Issue Resolution | Issues raised by government team during Hypercare receive priority response — 4-hour acknowledgement, 24-hour resolution target for operational issues. |
| Dashboard Review | Afronovation Customer Success reviews executive dashboard with government Tenant Admin and senior official at Week 4 and Week 8 to demonstrate intelligence value. |
| Dia Intelligence Introduction | Formal Dia AI capability demonstration at Week 4. Afronovation Customer Success runs first Dia query session with government analyst team. |
| First Intelligence Report | First executive intelligence report generated and reviewed with government programme director at Week 6. Report used as a model for ongoing ministerial briefings. |
| Hypercare Exit Review | At Week 8, Afronovation and government jointly review platform performance, registry growth, and team confidence. Hypercare exit criteria must be met before transitioning to steady state support. |

## 9.1 Hypercare Exit Criteria

- Registry has at least 200 verified registrant profiles

- Embassy Admin and Consular Officer teams are independently processing verifications

- Government Tenant Admin has created at least one report independently

- No outstanding critical or high-priority platform issues

- Government team has completed all training and confirmed confidence rating above 4/5

- First Dia AI intelligence query completed and reviewed with government analyst team

# 10. Phase 8 — Steady State & Long-Term Success

| Standard Support | Email and portal support for operational questions. Response SLA: 24 hours for standard issues, 4 hours for platform-affecting issues. |
| --- | --- |
| Quarterly Business Review | Quarterly 60-minute strategic review between Afronovation Account Manager and government programme director. Registry growth, intelligence utilisation, Dia forecast review, and roadmap discussion. |
| Annual Executive Briefing | Annual presentation to government senior leadership — Minister, DG, or Central Bank Governor level. Civis year-in-review, national diaspora intelligence summary, and strategic recommendations from Dia. |
| Platform Updates | Continuous platform improvements deployed per release schedule. Sovereign and Government tier clients notified 14 days before significant updates. Tenant Admin can schedule update windows. |
| Renewal Planning | Renewal discussion initiated 90 days before contract end. Account Manager presents growth summary, platform roadmap, and renewal commercial proposal. |
| Expansion Opportunities | Proactive identification of expansion opportunities — additional embassies, new platform modules (EmbassyOS, BridgeVault), additional languages, or tier migration to Civis Government or Sovereign. |

# 11. Pre-Implementation Checklist

This checklist must be completed and signed off by both the Afronovation Implementation Lead and the government Programme Director before any technical implementation work begins.

## 11.1 Legal & Commercial

| Status | Checklist Item | Owner |
| --- | --- | --- |
| ☐ | Sovereign client agreement executed and signed by authorised government representative | Commercial Team |
| ☐ | Data Processing Agreement executed and signed | Legal |
| ☐ | Deployment tier confirmed and documented | Commercial Team |
| ☐ | Payment terms agreed and first invoice issued | Commercial Team |
| ☐ | Data residency jurisdiction confirmed and documented | Legal + DevOps |
| ☐ | Applicable national data protection laws reviewed and compliance approach confirmed | Legal |

## 11.2 Government Readiness

| Status | Checklist Item | Owner |
| --- | --- | --- |
| ☐ | Tenant Admin identified and contact details confirmed | Customer Success |
| ☐ | Embassy Admin contacts identified for each embassy | Customer Success |
| ☐ | Government IT technical contact identified | Implementation Lead |
| ☐ | Executive programme sponsor confirmed | Commercial Team |
| ☐ | Existing data inventory completed and shared with Afronovation | Government + Implementation |
| ☐ | Branding assets received — logo, official platform name if applicable | Implementation Lead |
| ☐ | Custom domain name confirmed if applicable | Government IT + DevOps |
| ☐ | Embassy inventory list completed — all missions with host country, city, and coverage area | Government Tenant Admin |

## 11.3 Technical Readiness

| Status | Checklist Item | Owner |
| --- | --- | --- |
| ☐ | Hosting region confirmed and infrastructure provisioning plan approved | DevOps |
| ☐ | Environment variables and secrets prepared for deployment | Engineering |
| ☐ | Staging environment deployed and tested | DevOps |
| ☐ | Data residency test completed — data confirmed writing to correct region | DevOps + Legal |
| ☐ | Branding configuration applied and approved by government team | Design + Engineering |
| ☐ | Custom domain configured and TLS certificate issued | DevOps |
| ☐ | Tenant Admin account created and MFA enrolled | Platform Engineering |
| ☐ | All SQL packs executed in correct sequence on production database | Engineering |
| ☐ | RLS policies verified for all tenant-scoped tables | Engineering |

## 11.4 Data Migration Readiness

| Status | Checklist Item | Owner |
| --- | --- | --- |
| ☐ | Data export received from government in agreed format | Government IT |
| ☐ | Data quality assessment completed and report shared | Implementation Team |
| ☐ | Field mapping document approved by government Tenant Admin | Implementation + Government |
| ☐ | Test migration completed on staging and approved | Implementation + Government |
| ☐ | Full staging migration completed and government sign-off received | Implementation + Government |
| ☐ | Secure data transfer channel established for production migration | Engineering |

## 11.5 Go-Live Readiness

| Status | Checklist Item | Owner |
| --- | --- | --- |
| ☐ | All embassy records created and jurisdictions configured | Implementation Team |
| ☐ | All Embassy Admin accounts created, MFA enrolled, and training completed | Embassy Admin |
| ☐ | All Consular Officer accounts created and training completed | Embassy Admin |
| ☐ | Analyst and Economic Planner accounts created and training completed | Platform Engineering |
| ☐ | Executive Viewer accounts created and orientation completed | Customer Success |
| ☐ | Registrant portal tested end-to-end in English and French | Engineering |
| ☐ | Consent text reviewed and approved in correct languages | Legal + Government |
| ☐ | First registration campaign designed and approved | Government + Customer Success |
| ☐ | Monitoring dashboards active and reviewed | DevOps |
| ☐ | Go-live sign-off from government Programme Director received | Customer Success |

# 12. Post-Go-Live Success Milestones

The following milestones define success across the first year of Civis operation. These are shared with the government team at go-live as a joint success framework.

| Milestone | Success Criteria | Owner |
| --- | --- | --- |
| Week 4 | Tenant Admin has configured platform. At least 2 embassies active. First 10 test registrations completed. | Implementation Team |
| Week 8 | Embassy staff trained. At least 50 real registrations in system. First dashboard review completed by senior government official. | Customer Success |
| Week 12 | First registration campaign launched. 500+ registrations target. Dia forecasting previewed to government team. | Customer Success |
| Month 6 | 1,000+ verified registrations. Embassy verification workflow operational. First executive report generated and reviewed. | Account Manager |
| Month 12 | Registry showing consistent growth. Government team independently operating platform. Annual business review completed. Renewal discussion initiated. | Account Manager |
| Year 2+ | Registry established as operational national asset. Expansion to additional modules or embassies. Renewal or EA contract executed. | Commercial Team |

# 13. Common Implementation Risks & Mitigations

| Government IT Bandwidth | Government IT teams are often stretched across multiple initiatives. Risk: technical setup delayed. Mitigation: Afronovation handles all platform-side configuration. Government IT involvement limited to DNS, domain, and data export. Clear task list provided upfront. |
| --- | --- |
| Data Quality Issues | Existing embassy data is often incomplete, inconsistent, or heavily duplicated. Risk: migration takes longer than expected. Mitigation: Data quality assessment in Phase 1. Realistic timeline agreed before migration begins. Government team allocated for data cleaning if required. |
| Embassy Staff Resistance | Embassy staff may resist a new platform, especially if it changes existing workflows. Risk: low adoption. Mitigation: Embassy Admin training emphasises ease of use. First session demonstrates how Civis reduces manual work. Embassy Admins involved in jurisdiction configuration to build ownership. |
| Language Gaps | Government team may be primarily Francophone but platform launched in EN first. Risk: adoption friction. Mitigation: FR platform available in Phase 2. In the interim, training materials provided in FR. Afronovation Customer Success bilingual support available. |
| Procurement Delays | Government procurement processes can stall implementation even after contract execution. Risk: implementation timeline extended. Mitigation: technical setup can begin in parallel with outstanding procurement formalities where legally permitted. Clear milestone-based payment structure. |
| EmbassyOS Integration Expectation | Government may expect immediate EmbassyOS integration if Afronovation's EmbassyOS relationship is known. Risk: expectation mismatch. Mitigation: Phase 1 standalone embassy module is fully functional. EmbassyOS integration roadmap shared clearly. Integration activation timeline agreed in advance. |

# 14. Support Channels & Escalation

| Standard Support | Email: support@civis.afronovation.com. Response within 24 hours for standard queries. Available in English and French. |
| --- | --- |
| Priority Support | Available for Civis Government and Sovereign clients. Dedicated Slack or Teams channel. Response within 4 hours for operational issues. |
| Emergency Support | For P1 incidents — platform unavailable or data breach suspected. Phone and direct contact to on-call engineering. 24/7 during Hypercare period. Business hours thereafter unless contracted otherwise. |
| Training Support | Post-training questions supported via email for 4 weeks after training completion. Afronovation responds within 24 hours. |
| Account Management | Quarterly business reviews with dedicated Account Manager. Annual executive briefing. Renewal and expansion discussions via Account Manager. |
| Language Support | All support available in English and French. Afronovation support team bilingual EN/FR. Support tickets may be submitted in either language. |

# 15. Strategic Conclusion

A successful Civis implementation is one where the government team is proud of what they have built — a national intelligence asset that they operate independently, that produces insights that inform real decisions, and that grows in value as more diaspora citizens register and more intelligence is generated.

Afronovation's role in implementation is to transfer capability — not to create dependency. Every training session, every checklist, and every hypercare review should move the government team closer to independent operation and further from needing Afronovation to run the platform for them.

The measure of a successful Civis implementation is not a signed go-live certificate. It is a Minister of Foreign Affairs reviewing a Dia intelligence brief and saying: this is exactly what we needed to design our diaspora engagement strategy. Everything else in this playbook exists to make that moment possible.